## README
Meterbook — Plan, Test & Reliability Tracker
Meterbook: Usage-based billing and double-entry ledger for SaaS companies. Two tracks: the platform baseline every SaaS needs, then the product. Every task, test, metric, load run and chaos experiment is tracked here as evidence of reliability, not just functionality.
SETTINGS
Project start date | 2026-11-02
TRACKS
Platform | Platform baseline: auth, tenancy, API keys, RBAC, audit, quotas, CI/CD, infra
Product | Meterbook product: Usage-based billing and double-entry ledger for SaaS companies
HOW TO USE
1. Plan | Work top-down by Week. Set Status (dropdown) and % Complete as you go. Done forces 100%. Paste the PR / commit link in Evidence.
2. Test_Catalog | Reference of 40+ test types (black/white/grey box), what each proves, when it runs in CI, tools per language and the pass gate.
3. Test_Cases | Concrete test cases per project. After each run set Status, Last Run date, Actual Result and an Evidence link (CI run, report).
4. Metrics_SLOs | Targets are pre-filled. Type the measured value; Result computes PASS/FAIL against the target automatically.
5. Load_Stress_Runs | Planned load / stress / spike / soak / scalability / volume runs. Enter results from k6/Gatling/Locust; Result checks throughput, p99 and error rate against the SLO columns.
6. Chaos_Resilience | Fault-injection experiments. Enter observed behaviour, recovery time and data loss; Result checks against the RTO target.
7. Coverage | Line / branch / mutation scores per module, checked against targets.
8. Defects | Every bug found by a test: severity, test ID, root cause, fix PR, and whether a regression test was added.
9. Weekly_Log | One row per week: planned vs done (auto), hours, blockers, learnings, demo link.
10. Dashboard | Auto-calculated progress, test pass rates, SLO status and a Release Gate per track. Show this sheet to recruiters.
LEGEND
Blue text, yellow fill | Input cell — you edit these.
Black text | Formula or pre-filled plan content — leave formulas alone.
Grey italic row | EXAMPLE row showing the expected format. Excluded from every Dashboard total. Delete or keep.
Green / Red / Grey | PASS / FAIL / NOT RUN or PENDING result highlighting.
CONVENTIONS
Percentages | Enter as fractions or with %: 0.85 or 85% (not 85).
Latency | Milliseconds unless the Unit column says otherwise.
Error rate | Fraction of requests: 0.1% = 0.001.
Evidence | Every PASS should link to proof: CI run, Grafana snapshot, k6 HTML report, Chaos Mesh log. That link is what convinces a reviewer.
Targets | Targets are engineering goals chosen for these designs, not published industry standards. Tighten them once you have a baseline.
Note on C6: Assumption: start on the Monday after today (2026-10-23 is a Friday). Change this; every planned date in Plan and Weekly_Log moves with it.

## Dashboard
Meterbook Dashboard
All figures calculate from the other sheets. EXAMPLE rows are excluded.
Measure | Platform | Product | TOTAL
Project | Platform baseline: auth, tenancy, API keys, RBAC, audit, quotas, CI/CD, infra | Meterbook product: Usage-based billing and double-entry ledger for SaaS companies
DELIVERY PROGRESS
Tasks
Done
In Progress
Blocked
Overdue
Est. Hours
Hours Earned
% Complete (hours-weighted)
TESTING
Test Cases
Passed
Failed
Blocked
Not Run
Execution %
Pass Rate (of executed)
Automation %
SLOs & RELIABILITY
Metrics
Metrics PASS
Metrics FAIL
Metrics Pending
Load Runs
Load Runs PASS
Chaos Experiments
Chaos PASS
Coverage Modules PASS
QUALITY
Open Defects
Open S1/S2 Defects
RELEASE GATE
Release Gate = READY TO SHIP only when: all tasks done, every test case run with 0 failures/blocked, every metric measured and passing, every load run and chaos experiment passing, and 0 open S1/S2 defects.
TEST TYPE COVERAGE (cases per type, both tracks)
Test Type | Box | Cases | Passed | Failed | Not Run
Unit
Integration
Component / Service
Contract (consumer-driven)
API (schema-based)
Functional
End-to-End (E2E)
Smoke
Sanity
Regression
User Acceptance (UAT)
Boundary value / Equivalence partitioning
Statement / Branch coverage
Mutation
Static analysis / Lint
Property-based
Fuzz
Concurrency / Race
Idempotency
Data integrity / Invariant
Database migration
Compatibility (SDK / version)
Performance benchmark (micro)
Load
Stress / Breakpoint
Spike
Soak / Endurance
Scalability
Volume
Capacity planning
Chaos engineering
Failover / Disaster recovery
Backup & restore
Resilience patterns
Network partition (Jepsen-style)
Deployment / Rollback
SAST
SCA / Dependency & image scan
Secrets scanning
DAST
AuthN / AuthZ & tenant isolation
Penetration test (checklist)
Compliance / Audit
Observability / Alert test
Accessibility (portal)
Usability
ML / LLM quality evaluation
Amber = no test case of this type yet. Some types (load, chaos, coverage) are tracked on their own sheets instead.

## Plan
Task ID | Track | Phase | Task | Definition of Done | Priority | Est. Hours | Week # | Planned Start | Planned End | Status | % Complete (input) | Effective % | Actual Hours | Done Date | Schedule Flag | Evidence / PR Link | Notes
EX-001 | EXAMPLE | Core | Example: idempotency middleware | Duplicate POST returns stored response | P0 | 8 |  |  |  | Done | 100% |  | 9 | 2026-11-06 |  | https://github.com/you/repo/pull/42 | Example row — format only
MB-T01 | Platform | Design | Repo layout, coding standards, ADR template, design-doc template | Repo created; ADR-000 merged; templates in /docs | P1 | 6 | 1 |  |  | Done | 100% |  |  | 2026-10-23 |  | commit 19024d4 (branch foundation) | Engineering rules, README, CONTRIBUTING, ADR-0000/0001, design + runbook templates, coding/testing/API/git standards
MB-T02 | Platform | Design | SLO document template and error-budget policy | SLO template approved; policy says what happens when budget is spent | P1 | 4 | 1 |  |  | Done | 100% |  |  | 2026-10-23 |  | commit 19024d4 (branch foundation) | docs/slo/template.md (burn-rate alerting) + docs/slo/error-budget-policy.md
MB-T03 | Platform | Infra | Terraform AWS baseline: VPC, EKS, RDS, S3, IAM, remote state with locking | terraform plan/apply green from CI; state in S3 with native locking (ADR-0002) | P0 | 16 | 1 |  |  | In Progress | 85% |  |  |  |  | https://github.com/mhrj7/meterbook/pull/7 | In AWS (eu-north-1): GitHub OIDC provider and meterbook-terraform-apply role created; trust fixed to GitHub's immutable OIDC subjects after the first bootstrap run was rejected. GitHub environments dev/production limited to main. Stack merged to main (PRs #1-#6). Remaining: bootstrap run green (state bucket, plan role), then dev apply-verify-destroy once AWS finishes verifying the new account.
MB-T04 | Platform | Infra | Secrets management: Vault or AWS Secrets Manager + External Secrets Operator | No secrets in git (gitleaks passes); pods read secrets at runtime | P0 | 6 | 2 |  |  | In Progress | 90% |  |  |  |  | https://github.com/mhrj7/meterbook/actions/runs/39912053895 | Green CI incl. kind end-to-end (4/4: delivery, runtime read by a pod, rotation in 3s, namespace isolation) after fixing a false-green CI step and a moto crash. Remaining: verify on real AWS (secrets, ESO role, Pod Identity) once the AWS account finishes verification and dev is applied.
MB-T05 | Platform | CI/CD | GitHub Actions: lint, test, build, SBOM (Syft), image scan (Trivy), cosign signing | Pipeline < 10 min; fails on critical CVE | P0 | 12 | 2 |  |  | In Progress | 85% |  |  |  |  | https://github.com/mhrj7/meterbook/actions/runs/39905115436 | Green CI run on PR #3: 3.3 min wall clock (Terraform job 3.0 min). Done: ci.yml (Terraform fmt/validate/test/tflint/trivy, Gitleaks, actionlint, single ci check), reusable container.yml (Trivy CRITICAL gate, SBOM, cosign), Terraform plan/apply via OIDC, SHA-pinned actions, Dependabot, ADR-0003. Remaining: CRITICAL-CVE gate exercised by the first service image (MB-T07).
MB-T06 | Platform | CI/CD | Helm chart library + ArgoCD GitOps (dev / staging / prod) | Merge to main auto-syncs staging; prod via promotion PR | P0 | 12 | 2 |  |  | Not Started
MB-T07 | Platform | Identity | OIDC login (Keycloak/Zitadel), SAML SSO, SCIM provisioning | SSO e2e test passes with a test IdP | P0 | 20 | 3 |  |  | Not Started
MB-T08 | Platform | Tenancy | Tenant model org > project > env; Postgres row-level security | Cross-tenant access test fails closed | P0 | 12 | 3 |  |  | Not Started
MB-T09 | Platform | Security | Scoped, hashed API keys with rotation and revocation | Revoked key rejected within 60 s | P0 | 8 | 3 |  |  | Not Started
MB-T10 | Platform | Security | Service mesh mTLS (Linkerd or Istio) | Plaintext pod-to-pod traffic rejected | P1 | 8 | 4 |  |  | Not Started
MB-T11 | Platform | SaaS | RBAC + customer-facing audit log service | Every mutating endpoint emits an audit event | P0 | 12 | 4 |  |  | Not Started
MB-T12 | Platform | SaaS | Per-tenant rate limiting and quotas | 429 with Retry-After; quota visible in admin | P0 | 8 | 4 |  |  | Not Started
MB-T13 | Platform | SaaS | Dogfood: bill Meterbook's own customers with Meterbook (Stripe as payment provider) | Own subscriptions invoiced by Meterbook | P1 | 10 | 4 |  |  | Not Started
MB-T14 | Platform | Observability | OTel Collector, Prometheus, Grafana, Loki, Tempo; golden-signal dashboards | Every service has RED dashboard and trace links | P0 | 12 | 4 |  |  | Not Started
MB-T15 | Platform | Ops | Public status page, incident runbook template, on-call rotation doc | Status page live; runbook template used by product services | P2 | 4 | 4 |  |  | Not Started
MB-T16 | Product | Design | PRD + Google-style design doc (alternatives, trade-offs, capacity estimate) | Doc reviewed; open questions closed | P0 | 10 | 5 |  |  | Not Started
MB-T17 | Product | Design | Data model: accounts, ledger entries, invoices, money in minor units | ERD + ADR for ledger immutability and isolation level | P0 | 8 | 5 |  |  | Not Started
MB-T18 | Product | Design | API spec: OpenAPI (public) + protobuf (internal gRPC) | Spectral lint passes; buf breaking-change check in CI | P0 | 6 | 5 |  |  | Not Started
MB-T19 | Product | Core | Double-entry ledger service (append-only, Java 21 + Spring Boot 3 + jOOQ) | Invariant sum(debits)=sum(credits) enforced and tested | P0 | 24 | 6 |  |  | Not Started
MB-T20 | Product | Core | Idempotency-key middleware (Redis + Postgres) | Duplicate POST returns stored response; no duplicate effect | P0 | 8 | 6 |  |  | Not Started
MB-T21 | Product | Core | Usage-event ingestion API -> Kafka with dedupe by event_id | 10k events/s on staging; duplicates dropped | P0 | 20 | 7 |  |  | Not Started
MB-T22 | Product | Core | Pricing engine: tiered, volume, per-seat, prepaid credits, commitments | Rating rules 100% branch covered | P0 | 24 | 8 |  |  | Not Started
MB-T23 | Product | Core | Invoice generation: proration, multi-currency, tax hook | Invoices match golden files | P0 | 20 | 9 |  |  | Not Started
MB-T24 | Product | Core | Transactional outbox + Debezium CDC | No lost events when pod is killed after commit | P0 | 12 | 9 |  |  | Not Started
MB-T25 | Product | Core | Temporal workflows: dunning, payment retries, sagas with compensation | Compensation path tested for each saga step | P0 | 16 | 10 |  |  | Not Started
MB-T26 | Product | Core | Payment-provider adapter (Stripe) + inbound webhook verification | Signature verified; adapter interface allows a second PSP | P1 | 10 | 10 |  |  | Not Started
MB-T27 | Product | Core | Outbound webhooks: HMAC signing, retries w/ backoff, DLQ, replay API | Delivery success >= 99.9% under endpoint flakiness | P0 | 12 | 11 |  |  | Not Started
MB-T28 | Product | Core | Reconciliation job: ledger vs PSP payouts | Daily report with zero unexplained differences | P1 | 10 | 11 |  |  | Not Started
MB-T29 | Product | SaaS | Customer portal + internal admin console | E2E flows pass in Playwright | P1 | 16 | 12 |  |  | Not Started
MB-T30 | Product | SaaS | Generated SDKs (TypeScript, Python, Java) | Published to npm / PyPI / Maven (or GitHub Packages) | P2 | 8 | 12 |  |  | Not Started
MB-T31 | Product | Testing | Unit + property-based tests (jqwik) for ledger and pricing | Branch >= 90%, mutation (PIT) >= 75% | P0 | 16 | 12 |  |  | Not Started
MB-T32 | Product | Testing | Integration (Testcontainers) + contract tests (Pact) | All green in CI | P0 | 12 | 13 |  |  | Not Started
MB-T33 | Product | Testing | Load / stress / spike / soak runs (Gatling or k6) | All rows in Load_Stress_Runs filled | P0 | 12 | 13 |  |  | Not Started
MB-T34 | Product | Testing | Chaos experiments (Chaos Mesh) | All rows in Chaos_Resilience filled | P0 | 8 | 14 |  |  | Not Started
MB-T35 | Product | Security | Threat model (STRIDE) + DAST (ZAP) + pen-test checklist | No high findings open | P0 | 8 | 14 |  |  | Not Started
MB-T36 | Product | Ops | Canary rollout with Argo Rollouts + auto-rollback on SLO breach | Bad build rolled back automatically in a drill | P0 | 6 | 14 |  |  | Not Started
MB-T37 | Product | Launch | Docs site + 5-minute quickstart | A new user finishes the quickstart in < 5 min (timed) | P1 | 8 | 14 |  |  | Not Started
MB-T38 | Product | Launch | Public benchmark + reliability report (README + blog) | Report links Dashboard evidence | P1 | 6 | 14 |  |  | Not Started
Formulas:
Schedule Flag = IF([Status]="Done",IF([Done Date]="","Done",IF([Planned End]="","Done",IF([Done Date]<=[Planned End],"On time","Late"))),IF([Status]="Blocked","BLOCKED",IF([Planned Start]="","",IF(TODAY()>[Planned End],"OVERDUE",IF(TODAY()>=[Planned Start],"Active","Upcoming")))))

## Test_Catalog
Test Type | Category | Box | What It Proves | When It Runs | Tools — Java | Tools — Go | Tools — Rust | Tools — Python | Pass Gate | Evidence to Show
Unit | Functional | White | Each function/class behaves correctly in isolation | Pre-commit + every PR | JUnit 5, AssertJ, Mockito | testing, testify | cargo test | pytest | 100% pass; coverage targets met | CI run + coverage report
Integration | Functional | Grey | Components work with real DB/Kafka/Redis | Every PR | Testcontainers, Spring Boot Test | testcontainers-go | testcontainers-rs | testcontainers-python | 100% pass | CI run
Component / Service | Functional | Grey | One service works end-to-end with dependencies stubbed | Every PR | WireMock, RestAssured | httptest, gomock | wiremock-rs | respx, pytest-httpx | 100% pass | CI run
Contract (consumer-driven) | Functional | Black | API producer and consumers agree; no breaking changes | Every PR | Pact JVM | pact-go | pact_consumer | pact-python | All pacts verified; buf/oasdiff breaking check passes | Pact Broker matrix
API (schema-based) | Functional | Black | Every endpoint honours its OpenAPI spec | Every PR | RestAssured | Schemathesis (CLI) | Schemathesis (CLI) | Schemathesis | 0 spec violations, 0 5xx | Schemathesis report
Functional | Functional | Black | Features meet requirements from the user's view | Every PR / nightly | RestAssured, Cucumber | godog | cucumber-rs | pytest-bdd | 100% pass on P0 cases | Test report
End-to-End (E2E) | Functional | Black | Full user journeys across UI + APIs + workers | Nightly + pre-release | Playwright | Playwright | Playwright | Playwright | 100% pass on critical journeys | Playwright trace/video
Smoke | Functional | Black | Deployment is alive: health checks + 1 golden path | After every deploy | k6 / curl scripts | k6 | k6 | k6 | Pass within 2 min or auto-rollback | Deploy log
Sanity | Functional | Black | A specific fix works before full regression | Per hotfix | Targeted suite | Targeted suite | Targeted suite | Targeted suite | Pass | CI run
Regression | Functional | Black | Old features still work after changes | Nightly + pre-release | Full suite / golden files | Full suite / golden files | insta snapshots | syrupy snapshots | 0 new failures | Nightly report
User Acceptance (UAT) | Functional | Black | A target persona can do the job (e.g. finance closes month) | Pre-release | Scripted walkthrough | Scripted walkthrough | Scripted walkthrough | Scripted walkthrough | Persona signs off | Recorded demo
Boundary value / Equivalence partitioning | Functional | Black | Edges and classes of inputs behave correctly | Every PR | JUnit params | table-driven tests | rstest | pytest.mark.parametrize | All edges covered | Test list
Statement / Branch coverage | Structural | White | Code paths are actually exercised | Every PR | JaCoCo | go test -cover | cargo-llvm-cov | coverage.py | Line >= 85%, branch >= 80% | Coverage sheet + Codecov
Mutation | Structural | White | Tests catch real bugs, not just run code | Nightly | PIT (pitest) | go-mutesting | cargo-mutants | mutmut | Mutation score >= 70% | Mutation report
Static analysis / Lint | Structural | White | Code smells, bugs, style issues | Pre-commit + PR | SpotBugs, Error Prone, Checkstyle | golangci-lint, staticcheck | clippy | ruff, mypy | 0 errors | CI run
Property-based | Functional | White | Invariants hold for thousands of random inputs | Every PR | jqwik | rapid, gopter | proptest | Hypothesis | 0 counter-examples (seed logged) | CI run with seed
Fuzz | Security | White | Parsers/APIs don't crash on malformed input | Nightly (1 h) | Jazzer | go test -fuzz | cargo-fuzz | Atheris | 0 crashes in 1 h | Fuzz corpus + log
Concurrency / Race | Functional | White | No data races, lost updates, deadlocks | Every PR | jcstress, Lincheck | go test -race | loom, miri | pytest-xdist stress | 0 races | CI run
Idempotency | Functional | Grey | Retries never duplicate side effects | Every PR | Custom harness | Custom harness | Custom harness | Custom harness | Exactly one effect per key | Test report
Data integrity / Invariant | Functional | Grey | Business invariants hold (ledger balances, no lost ops) | Nightly + during chaos | Invariant checker job | Invariant checker job | Invariant checker job | Invariant checker job | 0 violations | Checker log
Database migration | Functional | Grey | Schema migrations up/down work on real data volume | Every PR touching schema | Flyway + Testcontainers | golang-migrate | sqlx migrate | Alembic | Zero-downtime; rollback works | CI run
Compatibility (SDK / version) | Functional | Black | Old clients keep working; SDKs interoperate | Pre-release | Matrix build | Matrix build | Matrix build | tox / nox | All matrix cells pass | Matrix report
Performance benchmark (micro) | Non-functional | White | Hot-path speed and allocations, tracked over time | Nightly | JMH | go test -bench, benchstat | criterion | pytest-benchmark | No regression > 5% | Benchmark history
Load | Non-functional | Black | System meets SLOs at expected peak traffic | Pre-release | Gatling | k6 | k6, Goose | Locust | p99 and error rate within SLO | k6/Gatling HTML report
Stress / Breakpoint | Non-functional | Black | Where it breaks and that it fails gracefully | Pre-release | Gatling | k6 | k6 | Locust | Graceful 429/503; no data loss; breaking point recorded | Report + Grafana snapshot
Spike | Non-functional | Black | Sudden traffic jumps are absorbed (autoscale, queues) | Pre-release | Gatling | k6 | k6 | Locust | Error rate < 1% during spike | Report
Soak / Endurance | Non-functional | Black | No memory leaks or slow degradation over hours | Weekly (8-24 h) | Gatling + JFR | k6 + pprof | k6 + heaptrack | Locust + memray | Memory growth < 5%; p99 stable | Grafana 24 h snapshot
Scalability | Non-functional | Black | Throughput grows near-linearly with nodes | Pre-release | Gatling | k6 | k6 | Locust | 2x nodes >= 1.7x throughput | Scaling chart
Volume | Non-functional | Black | Works with production-size data (TBs, millions of rows) | Pre-release | Data generator + suite | Data generator + suite | Data generator + suite | Data generator + suite | Query SLOs met at volume | Report
Capacity planning | Non-functional | Grey | Resources needed per unit of load; cost per tenant | Per release | Load + metrics | Load + metrics | Load + metrics | Load + metrics | Capacity model documented | Capacity sheet in design doc
Chaos engineering | Resilience | Grey | System keeps steady state when parts fail | Weekly game day | Chaos Mesh, Litmus | Chaos Mesh, Toxiproxy | Chaos Mesh, Toxiproxy | Chaos Mesh, Toxiproxy | Steady state holds; RTO met | Chaos_Resilience sheet
Failover / Disaster recovery | Resilience | Grey | Region/DB loss recovers within RTO/RPO | Quarterly drill | Runbook drill | Runbook drill | Runbook drill | Runbook drill | RTO and RPO met | Drill report
Backup & restore | Resilience | Grey | Backups actually restore | Monthly | pgBackRest / RDS snapshot | same | same | same | Restore verified with checksum | Restore log
Resilience patterns | Resilience | Grey | Timeouts, retries, circuit breakers, bulkheads work | Every PR | Resilience4j + Toxiproxy | Toxiproxy | Toxiproxy | Toxiproxy | Breaker opens/closes as configured | Test report
Network partition (Jepsen-style) | Resilience | Grey | Consistency guarantees hold under partitions | Pre-release | Jepsen / custom | Jepsen / custom | Jepsen / custom | Jepsen / custom | No guarantee violated | History analysis (Elle/Knossos)
Deployment / Rollback | Resilience | Grey | Canary detects bad builds and rolls back; zero-downtime deploys | Per release | Argo Rollouts analysis | same | same | same | Auto-rollback in drill; 0 dropped requests | Rollout log
SAST | Security | White | Vulnerable code patterns | Every PR | Semgrep, CodeQL | gosec, Semgrep | cargo-audit, Semgrep | Bandit, Semgrep | 0 high/critical | Scan report
SCA / Dependency & image scan | Security | White | Vulnerable dependencies and container images | Every PR + daily | Trivy, OWASP Dependency-Check | govulncheck, Trivy | cargo-audit, Trivy | pip-audit, Trivy | 0 critical CVEs | SBOM + scan report
Secrets scanning | Security | White | No credentials committed | Pre-commit + PR | gitleaks | gitleaks | gitleaks | gitleaks | 0 findings | CI run
DAST | Security | Black | Running app resists common web attacks | Nightly on staging | OWASP ZAP | OWASP ZAP | OWASP ZAP | OWASP ZAP | 0 high alerts | ZAP report
AuthN / AuthZ & tenant isolation | Security | Black | No cross-tenant access; RBAC enforced on every endpoint | Every PR | Custom suite | Custom suite | Custom suite | Custom suite | 0 cross-tenant leaks | Test report
Penetration test (checklist) | Security | Black | Manual attack per OWASP ASVS / API Top 10 | Pre-launch | Burp Suite | Burp Suite | Burp Suite | Burp Suite | No open high findings | Pen-test report
Compliance / Audit | Security | Grey | Audit logs, retention, data deletion meet SOC 2-style controls | Pre-launch | Control checklist | same | same | same | All controls evidenced | Control matrix
Observability / Alert test | Non-functional | Grey | Alerts fire, dashboards and traces are correct | Per release | Synthetic faults + promtool test | promtool test rules | promtool | promtool | Every SLO alert fires in test | Alert test log
Accessibility (portal) | Non-functional | Black | Customer portal is usable with assistive tech | Per release | axe-core + Playwright | same | same | same | 0 serious axe violations | axe report
Usability | Non-functional | Black | New user completes quickstart unaided | Pre-launch | Timed session | same | same | same | Quickstart < 5 min | Recording
ML / LLM quality evaluation | Functional | Black | RAG retrieval and answer quality; guardrail accuracy | Every PR touching prompts/retrieval | n/a | n/a | n/a | Ragas, DeepEval, promptfoo | Scores >= targets; no drop > 2% | Eval report

## Test_Cases
Test ID | Track | Test Type | Box | Component | Scenario | Expected Result | Tool | Priority | Automated (Y/N) | Status | Last Run | Actual Result | Defect ID | Evidence Link
EX-TC-001 | EXAMPLE | Idempotency |  | Payments API | Example: same key POSTed twice | One ledger entry | Custom harness | P0 | Y | Pass | 2026-11-10 | 1 entry, identical 201 responses |  | https://github.com/you/repo/actions/runs/123
TC-PLT-001 | Platform | Integration |  | Identity | OIDC login with test Keycloak realm | Token issued; claims include tenant_id and roles | Playwright + Testcontainers | P0 | Y | Not Run
TC-PLT-002 | Platform | AuthN / AuthZ & tenant isolation |  | Tenancy | Tenant A requests Tenant B resource by ID | 403/404; RLS blocks query; audit event logged | Custom suite | P0 | Y | Not Run
TC-PLT-003 | Platform | AuthN / AuthZ & tenant isolation |  | API keys | Use a revoked API key | 401 within 60 s of revocation | Custom suite | P0 | Y | Not Run
TC-PLT-004 | Platform | Functional |  | Rate limiting | Exceed tenant quota | 429 with Retry-After; other tenants unaffected | k6 | P0 | Y | Not Run
TC-PLT-005 | Platform | SAST |  | CI | Semgrep + CodeQL on every PR | 0 high/critical findings | Semgrep, CodeQL | P0 | Y | Not Run
TC-PLT-006 | Platform | SCA / Dependency & image scan |  | CI | Trivy scan of all images | 0 critical CVEs | Trivy | P0 | Y | Not Run
TC-PLT-007 | Platform | Secrets scanning |  | CI | gitleaks over full history | 0 findings | gitleaks | P0 | Y | Pass | 2026-10-23 | 0 findings across full history |  | https://github.com/mhrj7/meterbook/actions/runs/39905115436
TC-PLT-008 | Platform | DAST |  | Public API | ZAP baseline scan on staging | 0 high alerts | OWASP ZAP | P1 | Y | Not Run
TC-PLT-009 | Platform | Smoke |  | Deploy | Post-deploy health + golden path | All /healthz 200 within 2 min | k6 | P0 | Y | Not Run
TC-PLT-010 | Platform | Backup & restore |  | RDS | Restore latest snapshot to a fresh env | Data checksum matches; RPO <= 5 min | Runbook | P0 | Y | Not Run
TC-PLT-011 | Platform | Compliance / Audit |  | Audit log | Every mutating endpoint emits audit event | 100% of endpoints covered | Custom suite | P1 | Y | Not Run
TC-PLT-012 | Platform | Deployment / Rollback |  | ArgoCD | Deploy a build that fails health checks | Auto-rollback; no user-visible errors | Argo Rollouts | P0 | Y | Not Run
TC-PLT-013 | Platform | Static analysis / Lint |  | CI | golangci-lint, clippy, SpotBugs, ruff on all repos | 0 errors; PR blocked otherwise | Linters in CI | P0 | Y | Not Run
TC-PLT-014 | Platform | Statement / Branch coverage |  | CI | Coverage gate on every PR | PR blocked below Coverage sheet targets | Codecov | P0 | Y | Not Run
TC-PLT-015 | Platform | Sanity |  | Hotfix | Targeted suite for a hotfix before full regression | Passes in < 5 min | CI targeted job | P1 | Y | Not Run
TC-PLT-016 | Platform | Failover / Disaster recovery |  | RDS | Multi-AZ failover drill under load | RTO <= 2 min; no committed data lost | Runbook drill | P0 | Y | Not Run
TC-PLT-017 | Platform | Chaos engineering |  | Game day | Run every Chaos_Resilience experiment for P0 | All PASS | Chaos Mesh | P1 | Y | Not Run
TC-PLT-018 | Platform | Capacity planning |  | Platform | Measure CPU/mem/cost per 1,000 tenants | Capacity model in design doc | k6 + Cost Explorer | P2 | Y | Not Run
TC-PLT-019 | Platform | Penetration test (checklist) |  | Public API | OWASP ASVS L2 + API Top 10 checklist | No open high findings | Burp Suite | P0 | Y | Not Run
TC-MB-001 | Product | Unit |  | Pricing | Tiered price exactly at tier boundary | Exact amount in minor units | JUnit 5 | P0 | Y | Not Run
TC-MB-002 | Product | Property-based |  | Ledger | 10k random transaction sequences | sum(debits) == sum(credits) always | jqwik | P0 | Y | Not Run
TC-MB-003 | Product | Mutation |  | Pricing | PIT mutation run on pricing module | Mutation score >= 75% | PIT | P1 | Y | Not Run
TC-MB-004 | Product | Functional |  | API | Create customer -> subscribe -> ingest usage -> invoice | Invoice total matches golden file | RestAssured | P0 | Y | Not Run
TC-MB-005 | Product | Idempotency |  | Payments API | Same Idempotency-Key POSTed twice concurrently | One ledger entry; identical responses | Custom harness | P0 | Y | Not Run
TC-MB-006 | Product | Concurrency / Race |  | Ledger | 100 concurrent debits on one account | No overdraft; no lost updates | jcstress / harness | P0 | Y | Not Run
TC-MB-007 | Product | Contract (consumer-driven) |  | Webhooks | Consumer pact for invoice.paid event | Pact verified by provider | Pact JVM | P1 | Y | Not Run
TC-MB-008 | Product | Integration |  | Outbox | Kill pod after DB commit, before publish | Event delivered exactly once downstream | Testcontainers + Toxiproxy | P0 | Y | Not Run
TC-MB-009 | Product | Regression |  | Invoicing | Golden-file invoice suite (50 scenarios) | No diff | JUnit golden files | P0 | Y | Not Run
TC-MB-010 | Product | Boundary value / Equivalence partitioning |  | Currency | JPY (0 decimals) and KWD (3 decimals) | Correct rounding; no float math | JUnit params | P0 | Y | Not Run
TC-MB-011 | Product | Fuzz |  | Usage API | Malformed JSON and huge payloads | 4xx only; no 5xx or crash | Jazzer | P1 | Y | Not Run
TC-MB-012 | Product | End-to-End (E2E) |  | Portal | Customer updates payment method mid-dunning | Dunning stops; invoice paid | Playwright | P1 | Y | Not Run
TC-MB-013 | Product | Data integrity / Invariant |  | Reconciliation | Inject a PSP payout mismatch | Flagged in daily report | Invariant checker | P0 | Y | Not Run
TC-MB-014 | Product | AuthN / AuthZ & tenant isolation |  | Webhooks | Inbound webhook with tampered signature | Rejected 400; logged | Custom suite | P0 | Y | Not Run
TC-MB-015 | Product | Database migration |  | Schema | Migration on 10M-row ledger table | No lock > 1 s; rollback works | Flyway + Testcontainers | P1 | Y | Not Run
TC-MB-016 | Product | User Acceptance (UAT) |  | Billing | Finance persona runs month-end close | Persona signs off | Scripted walkthrough | P1 | Y | Not Run
TC-MB-017 | Product | Component / Service |  | Ledger service | Ledger service with PSP stubbed (WireMock) | All flows pass with stub faults injected | WireMock + RestAssured | P0 | Y | Not Run
TC-MB-018 | Product | API (schema-based) |  | Public API | Schemathesis over full OpenAPI spec | 0 spec violations; 0 5xx | Schemathesis | P0 | Y | Not Run
TC-MB-019 | Product | Accessibility (portal) |  | Portal | axe-core scan of every portal page | 0 serious violations | axe-core + Playwright | P2 | Y | Not Run
TC-MB-020 | Product | Usability |  | Docs | New developer completes quickstart unaided | < 5 min (timed) | Recorded session | P1 | Y | Not Run
TC-MB-021 | Product | Load |  | Ingestion | Execute run LR-MB-01 | Run PASS in Load_Stress_Runs | Gatling | P0 | Y | Not Run
TC-MB-022 | Product | Stress / Breakpoint |  | Ingestion | Execute run LR-MB-02 | Graceful 429s; breaking point recorded | Gatling | P0 | Y | Not Run
TC-MB-023 | Product | Spike |  | Invoice API | Execute run LR-MB-03 | Run PASS | Gatling | P1 | Y | Not Run
TC-MB-024 | Product | Soak / Endurance |  | All services | Execute run LR-MB-04 | Heap flat; p99 stable over 8 h | Gatling + JFR | P0 | Y | Not Run
TC-MB-025 | Product | Scalability |  | Ingestion | Execute run LR-MB-05 | >= 1.7x throughput at 2x nodes | Gatling | P1 | Y | Not Run
TC-MB-026 | Product | Volume |  | Invoicing | Execute run LR-MB-06 | 100k invoices in <= 15 min | Custom generator | P1 | Y | Not Run

## Metrics_SLOs
Metric ID | Track | Category | Metric | Comparator | Target | Unit | Measured (input) | Result | Measured By | Run Ref | Date | Evidence Link | Notes
EX-M-001 | EXAMPLE | Latency | Example: write API p99 | <= | 50 | ms | 38 |  | Gatling | EX-LR-001 | 2026-11-12 | https://grafana.example/d/abc
M-PLT-01 | Platform | Availability | Control-plane availability (30-day) | >= | 99.9% | % |  |  | Prometheus SLO
M-PLT-02 | Platform | Latency | Login / token issue p99 | <= | 300 | ms |  |  | k6
M-PLT-03 | Platform | Delivery (DORA) | CI pipeline duration | <= | 10 | min | 3.3 |  | GitHub Actions | 39905115436 | 2026-10-23 | https://github.com/mhrj7/meterbook/actions/runs/39905115436 | Wall clock from run created to last job completed, PR #3.
M-PLT-04 | Platform | Delivery (DORA) | Deployment frequency | >= | 5 | deploys/week |  |  | ArgoCD history
M-PLT-05 | Platform | Delivery (DORA) | Change failure rate | <= | 15% | % |  |  | Incident log
M-PLT-06 | Platform | Delivery (DORA) | Mean time to restore (MTTR) | <= | 30 | min |  |  | Incident log
M-PLT-07 | Platform | Security | Critical CVEs in deployed images | <= | 0 | count |  |  | Trivy
M-PLT-08 | Platform | Recovery | RPO (data loss window) | <= | 5 | min |  |  | Restore drill
M-PLT-09 | Platform | Recovery | RTO (time to restore) | <= | 30 | min |  |  | Restore drill
M-MB-01 | Product | Throughput | Usage-event ingestion | >= | 10000 | events/s |  |  | Gatling
M-MB-02 | Product | Latency | Write API p95 | <= | 25 | ms |  |  | Gatling
M-MB-03 | Product | Latency | Write API p99 | <= | 50 | ms |  |  | Gatling
M-MB-04 | Product | Errors | Error rate at peak load | <= | 0.1% | % |  |  | Gatling
M-MB-05 | Product | Correctness | Ledger drift after chaos (sum debits - credits) | <= | 0 | minor units |  |  | Invariant checker
M-MB-06 | Product | Correctness | Duplicate charges under retries | <= | 0 | count |  |  | Idempotency suite
M-MB-07 | Product | Reliability | Webhook delivery success | >= | 99.9% | % |  |  | Delivery log
M-MB-08 | Product | Latency | Outbox -> Kafka lag p99 | <= | 2 | s |  |  | Prometheus
M-MB-09 | Product | Batch | Invoice run for 100k customers | <= | 15 | min |  |  | Temporal metrics
M-MB-10 | Product | Quality | Branch coverage | >= | 90% | % |  |  | JaCoCo
M-MB-11 | Product | Quality | Mutation score | >= | 75% | % |  |  | PIT
M-MB-12 | Product | Availability | API availability (30-day) | >= | 99.95% | % |  |  | Prometheus SLO
Note on F1: Targets are engineering goals chosen for these designs, not published benchmarks.

## Load_Stress_Runs
Run ID | Track | Test Type | Scenario | Tool | Environment | Duration (min) | Target Load | Achieved Load | p50 (ms) | p95 (ms) | p99 (ms) | p99.9 (ms) | Error Rate | Max CPU % | Max Memory (GB) | SLO p99 (ms) | SLO Max Error | Attainment | Result | Date | Breaking Point / Observations | Evidence Link
EX-LR-001 | EXAMPLE | Load | Example: ingestion at 10k events/s | Gatling | staging | 30 | 10000 | 10450 | 8 | 21 | 38 | 95 | 0.03% | 68% | 3.1 | 50 | 0.1% |  |  | 2026-11-12 | Kafka consumer lag peaked at 1.2 s | https://grafana.example/d/abc
LR-PLT-01 | Platform | Load | Auth: 500 logins/s for 15 min | k6 | staging: 3 x m6i.large | 15 | 500 | [8 empty] | 300 | 0.1%
LR-PLT-02 | Platform | Spike | Auth: 0 -> 2,000 logins/s in 10 s | k6 | staging | 5 | 2000 | [8 empty] | 800 | 1%
LR-MB-01 | Product | Load | Usage ingestion at 10k events/s | Gatling | staging: 6 x m6i.xlarge, MSK 3 brokers | 30 | 10000 | [8 empty] | 50 | 0.1%
LR-MB-02 | Product | Stress / Breakpoint | Ramp ingestion until SLO breach (target = expected peak x3) | Gatling | staging | 30 | 30000 | [8 empty] | 200 | 1%
LR-MB-03 | Product | Spike | Invoice API 0 -> 5k RPS in 10 s | Gatling | staging | 5 | 5000 | [8 empty] | 150 | 1%
LR-MB-04 | Product | Soak / Endurance | 60% peak for 8 h | Gatling + JFR | staging | 480 | 6000 | [8 empty] | 50 | 0.1%
LR-MB-05 | Product | Scalability | Double app nodes 6 -> 12; expect >= 1.7x throughput | Gatling | staging | 30 | 17000 | [8 empty] | 50 | 0.1%
LR-MB-06 | Product | Volume | Invoice run on 100k customers / 50M usage rows | Custom generator | staging | 15 | 100000 | [8 empty] | 0 | 0%
Note on H1: Unit depends on the scenario: RPS, events/s, spans/s, connections, or rows. Achieved Load must use the same unit.
Note on Q1: 0 = no latency SLO for this run (judged on throughput and errors only).

## Chaos_Resilience
Experiment ID | Track | Fault Injected | Steady-State Hypothesis | Injection Method | Blast Radius | Expected Behaviour | Observed Behaviour (input) | Recovery Time (s) | Target RTO (s) | Data Loss? (Y/N) | Date | Result | Evidence Link
EX-CH-001 | EXAMPLE | Kafka broker loss | Zero lost events | PodChaos | Ingestion | Producer retries | Lag spike 4 s; all events delivered | 12 | 30 | N | 2026-11-14 |  | https://github.com/you/repo/blob/main/chaos/kafka.md
CH-PLT-01 | Platform | Primary DB failover | Control plane serves logins with < 1% errors | RDS reboot with failover | Control plane | Multi-AZ failover; connection pool reconnects |  |  | 120
CH-PLT-02 | Platform | Identity provider down | Existing sessions keep working | Scale Keycloak to 0 | Login only | Cached JWKS; new logins fail with clear error |  |  | 0
CH-MB-01 | Product | Kafka broker loss | Usage ingestion continues; zero lost events | Chaos Mesh PodChaos on 1 of 3 brokers | Ingestion | Producer retries; ISR keeps writes durable |  |  | 30
CH-MB-02 | Product | App pod kill mid-transaction | Ledger stays balanced | PodChaos kill every 30 s for 10 min | Ledger service | Txn rolls back or commits atomically; outbox replays |  |  | 10
CH-MB-03 | Product | Postgres latency 500 ms | API p99 degrades but no errors > 1% | Toxiproxy latency | Ledger DB | Timeouts + breaker; idempotent retries |  |  | 60
CH-MB-04 | Product | PSP (Stripe) outage | Payments queued, retried later; no double charge | Toxiproxy 100% 503 | Payment adapter | Temporal retries with backoff |  |  | 300
CH-MB-05 | Product | Redis loss (idempotency store) | No duplicate charges | Delete Redis pod | Idempotency | Fallback to Postgres idempotency table |  |  | 30
Note on J1: 0 = no service interruption allowed (recovery must be immediate).

## Coverage
Track | Module | Language | Tool | Line % (input) | Branch % (input) | Mutation % (input) | Target Line % | Target Branch % | Target Mutation % | Result | Date | Evidence Link
EXAMPLE | ledger | Java | JaCoCo + PIT | 93% | 88% | 79% | 90% | 85% | 75% |  | 2026-11-20 | https://app.codecov.io/gh/you/repo
Platform | identity | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Platform | tenancy | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Product | ledger | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Product | pricing | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Product | invoicing | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Product | webhooks | Java | JaCoCo + PIT |  |  |  | 90% | 85% | 75%
Note on H1: Money-handling product: stricter targets 90/85/75.

## Defects
Defect ID | Track | Title | Severity | Found By (Test ID) | Status | Opened | Closed | Days Open | Root Cause | Fix PR | Regression Test Added (Y/N)
EX-D-001 | EXAMPLE | Duplicate ledger entry when two retries race | S1-Critical | TC-MB-005 | Closed | 2026-11-10 | 2026-11-11 |  | Idempotency check and insert not in one transaction | https://github.com/you/repo/pull/57 | Y
Formulas:
Days Open = IF([Opened]="","",IF([Closed]="",TODAY()-[Opened],[Closed]-[Opened]))

## Weekly_Log
Week # | Week Start | Focus Track | Planned Tasks | Tasks Done | Planned Hours | Hours Logged (input) | Wins / Demo | Blockers | Learnings | Evidence Link
1 |  | Platform
2 |  | Platform
3 |  | Platform
4 |  | Platform
5 |  | Product
6 |  | Product
7 |  | Product
8 |  | Product
9 |  | Product
10 |  | Product
11 |  | Product
12 |  | Product
13 |  | Product
14 |  | Product